## Control_Panel
Control Panel
Application entry point. Button cells identify macro actions after VBA import.
Action | Macro / Target | Status / Notes
Refresh All | RefreshAll | Rebuilds register, buildup, cash flow, escalation, contingency, dashboard and QA
Build Cost Register | BuildCostRegister | Header-based macro; reads input sheets only
Run QA | RunQA | Writes PASS/FAIL to QA_Checks
Run Monte Carlo | RunMonteCarlo | Populates MonteCarlo_Results only; does not touch charts
Load Demo Project | LoadDemoProject | Reloads 40 M€ demo dataset
Reset Demo Data | ResetDemoData | Clears demo input/output areas
Last Refresh |  | 2026-06-03 14:03:33
Last QA Status
Cost Items
Base Cost EUR
Total Project Cost EUR
Key sheet | Purpose
Project_Setup | Project metadata and defaults
Cost_Register | Single source of truth
Estimate_Summary | Executive output
Dashboard | Charts and KPI overview
QA_Checks | Gate status
ReadMe | Use instructions
Release_Notes | Limitations and next steps
VBA source | See exported .bas file
Configurable Parameter | Source / Macro Use | Value
Data Mode | LoadDemoProject / ResetDemoData
Monte Carlo Iterations | RunMonteCarlo
Standard Hours per Month | Resource_Rates / Manpower
Project Duration Months | CashFlow / Manpower / Charts
Annual Escalation Rate | CalculateCashFlow / CalculateEscalation
Selected Contingency Method | CalculateContingency
Release Package | Workbook is xlsx; VBA provided as .bas for import into Excel | See Release_Notes
Final Status | Automated tests performed in artifact environment | Candidate - Excel desktop VBA import required

## Project_Setup
Project Setup
Primary project metadata and global defaults.
Project Name | Industrial CAPEX Demo Project - Clean Build RC8
Project Code | CAPEX-RC8-DEMO
Estimate Date | 2026-06-03
Estimate Class | Class 3
Project Phase | FEED
Base Currency | EUR
Project Start Date | 46204
Project End Date | 2029-06-30
Project Duration Months
Base Cost Target EUR | 40000000
Default Contingency Method | Monte Carlo P80 - Base Cost
Default Annual Escalation | 0.03
Excel Target | Microsoft Excel desktop Windows
Build Rule | Clean rebuild from functional references only
Data Mode | Demo
Monte Carlo Iterations | 10000
Standard Hours per Month | 160
Max Cash Flow Months | 60
RC8.1 Status | Patched workbook + corrected VBA module supplied separately

## Basis_of_Estimate
Basis of Estimate
Configurable AACE-style estimate classes and accuracy ranges.
Estimate Class | Description | Low Accuracy % | High Accuracy % | Typical Deliverables | Configurable | Default Contingency Range | Notes
Class 5 | Concept Screening | -50% | 100% | Stage gate package, scope definition, quantity maturity, vendor inputs | Yes | 10%–25% | Used by all input sheets
Class 4 | Concept Selection | -30% | 50% | Stage gate package, scope definition, quantity maturity, vendor inputs | Yes | 10%–25% | Used by all input sheets
Class 3 | FEED | -20% | 30% | Stage gate package, scope definition, quantity maturity, vendor inputs | Yes | 8%–15% | Used by all input sheets
Class 2 | Pre-Execution | -15% | 20% | Stage gate package, scope definition, quantity maturity, vendor inputs | Yes | 8%–15% | Used by all input sheets
Class 1 | Definitive Estimate | -10% | 15% | Stage gate package, scope definition, quantity maturity, vendor inputs | Yes | 8%–15% | Used by all input sheets

## WBS_CBS
WBS / CBS
Standard breakdown structure used across Cost_Register and reports.
WBS | WBS Description | CBS | CBS Description | Default Discipline | Default Phase | WBS Display | Active | Notes | Default Cost Category | Default Spend Category | Default Spend Curve | Default Contingency Eligible | Default Escalation Eligible
1.0 | Project Management | PM | Project Management | Project Management | Engineering | 1.0 - Project Management | Yes | Clean build standard list | Indirect Cost | Engineering | Bell Curve | Yes | Yes
2.0 | Engineering | ENG | Engineering | Project Management | Engineering | 2.0 - Engineering | Yes | Clean build standard list | Indirect Cost | Engineering | Bell Curve | Yes | Yes
3.0 | Procurement | PROC | Procurement | Procurement | Procurement | 3.0 - Procurement | Yes | Clean build standard list | Indirect Cost | Procurement | Linear | Yes | Yes
4.0 | Equipment | EQP | Equipment | Mechanical | Procurement | 4.0 - Equipment | Yes | Clean build standard list | Direct Cost | Procurement | Back Loaded | Yes | Yes
5.0 | Bulk Materials | BULK | Bulk Materials | Piping | Procurement | 5.0 - Bulk Materials | Yes | Clean build standard list | Direct Cost | Procurement | Linear | Yes | Yes
6.0 | Civil & Structural | CIV | Civil | Civil | Construction | 6.0 - Civil & Structural | Yes | Clean build standard list | Direct Cost | Construction | Front Loaded | Yes | Yes
7.0 | Electrical | ELE | Electrical | Electrical | Construction | 7.0 - Electrical | Yes | Clean build standard list | Direct Cost | Construction | Bell Curve | Yes | Yes
8.0 | Instrumentation & Automation | I&A | Instrumentation & Automation | Instrumentation | Construction | 8.0 - Instrumentation & Automation | Yes | Clean build standard list | Direct Cost | Construction | Bell Curve | Yes | Yes
9.0 | Construction | CON | Construction | Construction | Construction | 9.0 - Construction | Yes | Clean build standard list | Direct Cost | Construction | Bell Curve | Yes | Yes
10.0 | Commissioning & Start-up | COM | Commissioning | Commissioning | Commissioning | 10.0 - Commissioning & Start-up | Yes | Clean build standard list | Direct Cost | Commissioning | Back Loaded | Yes | Yes
11.0 | Owner Costs | OWN | Owner Costs | Owner | Other | 11.0 - Owner Costs | Yes | Clean build standard list | Owner Cost | Other | Front Loaded | Yes | Yes
12.0 | Other Costs | OTH | Other Costs | Other | Other | 12.0 - Other Costs | Yes | Clean build standard list | Other Cost | Other | Back Loaded | Yes | Yes

## FX_Rates
FX Rates
Configurable rate to EUR. EUR is the base currency.
Currency | Rate to EUR | Source / Notes | Last Updated | Active | QA
EUR | 1 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
USD | 0.92 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
GBP | 1.17 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
CHF | 1.04 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
DKK | 0.134 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
SEK | 0.087 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
NOK | 0.086 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
PLN | 0.235 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
TRY | 0.028 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS
MAD | 0.092 | Demo static rate. Replace with approved project FX. | 2026-06-03 | Yes | PASS

## Lists_Config
Lists Config
Central dropdown values. Input sheets use these lists.
Discipline | Cost Category | Cost Type | Phase | Y/N | Currency | Estimate Basis | Spend Category | Spend Curve | Unit | Location
Process | Direct Cost | Equipment | Engineering | Yes | EUR | Class 5 | Engineering | Linear | lot | Spain
Mechanical | Indirect Cost | Bulk Material | Procurement | No | USD | Class 4 | Procurement | Front Loaded | each | France
Piping | Owner Cost | Construction | Construction |  | GBP | Class 3 | Construction | Back Loaded | m | Germany
Civil | Manpower Cost | Engineering | Commissioning |  | CHF | Class 2 | Commissioning | Bell Curve | m2 | Italy
Electrical | Other Cost | EPCM | Other |  | DKK | Class 1 | Other | Manual | m3 | Netherlands
Instrumentation |  | Owner |  |  | SEK |  |  |  | kg | Belgium
Automation |  | Labour |  |  | NOK |  |  |  | ton | UK
Construction |  | Freight |  |  | PLN |  |  |  | h | Poland
Project Management |  | Spares |  |  | TRY |  |  |  | month | Remote
Procurement |  | Other |  |  | MAD |  |  |  | FTE-month
HSE
Commissioning
Owner
Other

## Data_Dictionary
Data Dictionary
Column-level definition of operational sheets.
Sheet | Column | Description | Type | Required | Input / Formula / Macro | Source | Validation | Used By | Notes
Equipment_Estimate | Item ID | Item ID for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Description | Description for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Discipline | Discipline for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | WBS | WBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | CBS | CBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Cost Category | Cost Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Cost Type | Cost Type for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Quantity | Quantity for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Unit | Unit for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Unit Rate | Unit Rate for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Currency | Currency for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | FX Rate | FX Rate for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Base Cost | Base Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Base Cost EUR | Base Cost EUR for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Estimate Basis | Estimate Basis for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Accuracy Low % | Accuracy Low % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Accuracy High % | Accuracy High % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Low Cost | Low Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Most Likely Cost | Most Likely Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | High Cost | High Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Contingency Eligible | Contingency Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Escalation Eligible | Escalation Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Spend Category | Spend Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Phase | Phase for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Start Month | Start Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | End Month | End Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Spend Curve | Spend Curve for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Equipment_Estimate | Notes | Notes for elementary cost item | Text/Number | No | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Item ID | Item ID for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Description | Description for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Discipline | Discipline for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | WBS | WBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | CBS | CBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Cost Category | Cost Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Cost Type | Cost Type for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Quantity | Quantity for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Unit | Unit for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Unit Rate | Unit Rate for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Currency | Currency for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | FX Rate | FX Rate for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Base Cost | Base Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Base Cost EUR | Base Cost EUR for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Estimate Basis | Estimate Basis for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Accuracy Low % | Accuracy Low % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Accuracy High % | Accuracy High % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Low Cost | Low Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Most Likely Cost | Most Likely Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | High Cost | High Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Contingency Eligible | Contingency Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Escalation Eligible | Escalation Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Spend Category | Spend Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Phase | Phase for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Start Month | Start Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | End Month | End Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Spend Curve | Spend Curve for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Electrical_Estimate | Notes | Notes for elementary cost item | Text/Number | No | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Item ID | Item ID for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Description | Description for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Discipline | Discipline for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | WBS | WBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | CBS | CBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Cost Category | Cost Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Cost Type | Cost Type for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Quantity | Quantity for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Unit | Unit for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Unit Rate | Unit Rate for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Currency | Currency for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | FX Rate | FX Rate for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Base Cost | Base Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Base Cost EUR | Base Cost EUR for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Estimate Basis | Estimate Basis for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Accuracy Low % | Accuracy Low % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Accuracy High % | Accuracy High % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Low Cost | Low Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Most Likely Cost | Most Likely Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | High Cost | High Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Contingency Eligible | Contingency Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Escalation Eligible | Escalation Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Spend Category | Spend Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Phase | Phase for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Start Month | Start Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | End Month | End Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Spend Curve | Spend Curve for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Instrumentation_Automation | Notes | Notes for elementary cost item | Text/Number | No | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Item ID | Item ID for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Description | Description for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Discipline | Discipline for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | WBS | WBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | CBS | CBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Cost Category | Cost Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Cost Type | Cost Type for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Quantity | Quantity for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Unit | Unit for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Unit Rate | Unit Rate for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Currency | Currency for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | FX Rate | FX Rate for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Base Cost | Base Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Base Cost EUR | Base Cost EUR for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Estimate Basis | Estimate Basis for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Accuracy Low % | Accuracy Low % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Accuracy High % | Accuracy High % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Low Cost | Low Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Most Likely Cost | Most Likely Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | High Cost | High Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Contingency Eligible | Contingency Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Escalation Eligible | Escalation Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Spend Category | Spend Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Phase | Phase for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Start Month | Start Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | End Month | End Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Spend Curve | Spend Curve for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Bulk_Materials_QTO | Notes | Notes for elementary cost item | Text/Number | No | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Item ID | Item ID for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Description | Description for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Discipline | Discipline for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | WBS | WBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | CBS | CBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Cost Category | Cost Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Cost Type | Cost Type for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Quantity | Quantity for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Unit | Unit for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Unit Rate | Unit Rate for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Currency | Currency for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | FX Rate | FX Rate for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Base Cost | Base Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Base Cost EUR | Base Cost EUR for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Estimate Basis | Estimate Basis for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Accuracy Low % | Accuracy Low % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Accuracy High % | Accuracy High % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Low Cost | Low Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Most Likely Cost | Most Likely Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | High Cost | High Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Contingency Eligible | Contingency Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Escalation Eligible | Escalation Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Spend Category | Spend Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Phase | Phase for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Start Month | Start Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | End Month | End Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Spend Curve | Spend Curve for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Construction_Estimate | Notes | Notes for elementary cost item | Text/Number | No | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Item ID | Item ID for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Description | Description for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Discipline | Discipline for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | WBS | WBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | CBS | CBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Cost Category | Cost Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Cost Type | Cost Type for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Quantity | Quantity for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Unit | Unit for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Unit Rate | Unit Rate for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Currency | Currency for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | FX Rate | FX Rate for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Base Cost | Base Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Base Cost EUR | Base Cost EUR for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Estimate Basis | Estimate Basis for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Accuracy Low % | Accuracy Low % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Accuracy High % | Accuracy High % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Low Cost | Low Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Most Likely Cost | Most Likely Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | High Cost | High Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Contingency Eligible | Contingency Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Escalation Eligible | Escalation Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Spend Category | Spend Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Phase | Phase for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Start Month | Start Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | End Month | End Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Spend Curve | Spend Curve for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Indirect_Owner_Costs | Notes | Notes for elementary cost item | Text/Number | No | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Item ID | Item ID for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Description | Description for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Discipline | Discipline for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | WBS | WBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | CBS | CBS for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Cost Category | Cost Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Cost Type | Cost Type for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Quantity | Quantity for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Unit | Unit for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Unit Rate | Unit Rate for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Currency | Currency for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | FX Rate | FX Rate for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Base Cost | Base Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Base Cost EUR | Base Cost EUR for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Estimate Basis | Estimate Basis for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Accuracy Low % | Accuracy Low % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Accuracy High % | Accuracy High % for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Low Cost | Low Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Most Likely Cost | Most Likely Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | High Cost | High Cost for elementary cost item | Text/Number | Yes | Formula | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Contingency Eligible | Contingency Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Escalation Eligible | Escalation Eligible for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Spend Category | Spend Category for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Phase | Phase for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Start Month | Start Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | End Month | End Month for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Spend Curve | Spend Curve for elementary cost item | Text/Number | Yes | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Other_Costs | Notes | Notes for elementary cost item | Text/Number | No | Input | User / Config | Lists_Config / formula | BuildCostRegister, QA, Summary | Header-based mapping required
Resource_Rates | Role | Role field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | Discipline | Discipline field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | Location | Location field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | Currency | Currency field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | Hourly Rate | Hourly Rate field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | Hours per Month | Hours per Month field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | Monthly Rate | Monthly Rate field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | FX Rate | FX Rate field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | Monthly Rate EUR | Monthly Rate EUR field | Text/Number | Yes | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Resource_Rates | Notes | Notes field | Text/Number | No | Input/Formula | User / FX_Rates | Lists_Config | Manpower_Plan
Cost_Register | Source Sheet | Source Sheet normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Source Row | Source Row normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Item ID | Item ID normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Description | Description normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Discipline | Discipline normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | WBS | WBS normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | CBS | CBS normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Cost Category | Cost Category normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Cost Type | Cost Type normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Quantity | Quantity normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Unit | Unit normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Unit Rate | Unit Rate normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Currency | Currency normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | FX Rate | FX Rate normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Base Cost | Base Cost normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Base Cost EUR | Base Cost EUR normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Estimate Basis | Estimate Basis normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Accuracy Low % | Accuracy Low % normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Accuracy High % | Accuracy High % normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Low Cost | Low Cost normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Most Likely Cost | Most Likely Cost normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | High Cost | High Cost normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Contingency Eligible | Contingency Eligible normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Escalation Eligible | Escalation Eligible normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Spend Category | Spend Category normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Phase | Phase normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Start Month | Start Month normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | End Month | End Month normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Spend Curve | Spend Curve normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth
Cost_Register | Notes | Notes normalized field | Text/Number | Yes | Macro Output | Input Sheets | Header validation | All reports | Single source of truth

## Equipment_Estimate
Equipment Estimate
User input layer. Cost_Register must be rebuilt from these sheets via BuildCostRegister.
Item ID | Description | Discipline | WBS | CBS | Cost Category | Cost Type | Quantity | Unit | Unit Rate | Currency | FX Rate | Base Cost | Base Cost EUR | Estimate Basis | Accuracy Low % | Accuracy High % | Low Cost | Most Likely Cost | High Cost | Contingency Eligible | Escalation Eligible | Spend Category | Phase | Start Month | End Month | Spend Curve | Notes
EQ-001 | Process mixer package |  | 4.0 |  |  | Equipment | 1 | lot | 2800000 | EUR |  |  |  | Class 3 | [9 empty] | 8 | 18
EQ-002 | Process vessels and tanks |  | 4.0 |  |  | Equipment | 1 | lot | 3200000 | EUR |  |  |  | Class 3 | [9 empty] | 6 | 18
EQ-003 | Pumping and transfer skids |  | 4.0 |  |  | Equipment | 1 | lot | 2000000 | EUR |  |  |  | Class 3 | [9 empty] | 10 | 20
EQ-004 | Heat exchangers and utility skids |  | 4.0 |  |  | Equipment | 1 | lot | 2400000 | EUR |  |  |  | Class 3 | [9 empty] | 9 | 21
EQ-005 | Equipment installation auxiliaries |  | 4.0 |  |  | Equipment | 1 | lot | 1600000 | EUR |  |  |  | Class 3 | [9 empty] | 14 | 27

## Electrical_Estimate
Electrical Estimate
User input layer. Cost_Register must be rebuilt from these sheets via BuildCostRegister.
Item ID | Description | Discipline | WBS | CBS | Cost Category | Cost Type | Quantity | Unit | Unit Rate | Currency | FX Rate | Base Cost | Base Cost EUR | Estimate Basis | Accuracy Low % | Accuracy High % | Low Cost | Most Likely Cost | High Cost | Contingency Eligible | Escalation Eligible | Spend Category | Phase | Start Month | End Month | Spend Curve | Notes
EL-001 | MV/LV substation package |  | 7.0 |  |  | Equipment | 1 | lot | 1400000 | EUR |  |  |  | Class 3 | [9 empty] | 8 | 18
EL-002 | MCC and distribution boards |  | 7.0 |  |  | Equipment | 1 | lot | 1200000 | EUR |  |  |  | Class 3 | [9 empty] | 9 | 20
EL-003 | Cable trays, cabling and termination |  | 7.0 |  |  | Bulk Material | 1 | lot | 1600000 | EUR |  |  |  | Class 3 | [9 empty] | 15 | 30
EL-004 | Lighting, earthing and small power |  | 7.0 |  |  | Construction | 1 | lot | 800000 | EUR |  |  |  | Class 3 | [9 empty] | 18 | 31

## Instrumentation_Automation
Instrumentation Automation
User input layer. Cost_Register must be rebuilt from these sheets via BuildCostRegister.
Item ID | Description | Discipline | WBS | CBS | Cost Category | Cost Type | Quantity | Unit | Unit Rate | Currency | FX Rate | Base Cost | Base Cost EUR | Estimate Basis | Accuracy Low % | Accuracy High % | Low Cost | Most Likely Cost | High Cost | Contingency Eligible | Escalation Eligible | Spend Category | Phase | Start Month | End Month | Spend Curve | Notes
IA-001 | PLC/DCS hardware and software |  | 8.0 |  |  | Equipment | 1 | lot | 1200000 | EUR |  |  |  | Class 3 | [9 empty] | 8 | 22
IA-002 | Field instrumentation and valves |  | 8.0 |  |  | Equipment | 1 | lot | 1000000 | EUR |  |  |  | Class 3 | [9 empty] | 10 | 25
IA-003 | Automation engineering and commissioning |  | 8.0 |  |  | Engineering | 1 | lot | 800000 | EUR |  |  |  | Class 3 | [9 empty] | 4 | 35

## Bulk_Materials_QTO
Bulk Materials QTO
User input layer. Cost_Register must be rebuilt from these sheets via BuildCostRegister.
Item ID | Description | Discipline | WBS | CBS | Cost Category | Cost Type | Quantity | Unit | Unit Rate | Currency | FX Rate | Base Cost | Base Cost EUR | Estimate Basis | Accuracy Low % | Accuracy High % | Low Cost | Most Likely Cost | High Cost | Contingency Eligible | Escalation Eligible | Spend Category | Phase | Start Month | End Month | Spend Curve | Notes
BM-001 | Process piping supply |  | 5.0 |  |  | Bulk Material | 1 | lot | 2100000 | EUR |  |  |  | Class 3 | [9 empty] | 10 | 25
BM-002 | Manual and control valves |  | 5.0 |  |  | Bulk Material | 1 | lot | 1100000 | EUR |  |  |  | Class 3 | [9 empty] | 9 | 24
BM-003 | Insulation, painting and tracing |  | 5.0 |  |  | Bulk Material | 1 | lot | 800000 | EUR |  |  |  | Class 3 | [9 empty] | 18 | 33

## Construction_Estimate
Construction Estimate
User input layer. Cost_Register must be rebuilt from these sheets via BuildCostRegister.
Item ID | Description | Discipline | WBS | CBS | Cost Category | Cost Type | Quantity | Unit | Unit Rate | Currency | FX Rate | Base Cost | Base Cost EUR | Estimate Basis | Accuracy Low % | Accuracy High % | Low Cost | Most Likely Cost | High Cost | Contingency Eligible | Escalation Eligible | Spend Category | Phase | Start Month | End Month | Spend Curve | Notes
CN-001 | Civil works and foundations |  | 6.0 |  |  | Construction | 1 | lot | 2000000 | EUR |  |  |  | Class 3 | [9 empty] | 12 | 26
CN-002 | Mechanical installation works |  | 9.0 |  |  | Construction | 1 | lot | 2300000 | EUR |  |  |  | Class 3 | [9 empty] | 18 | 31
CN-003 | Electrical installation works |  | 9.0 |  |  | Construction | 1 | lot | 1200000 | EUR |  |  |  | Class 3 | [9 empty] | 18 | 32
CN-004 | Pre-commissioning and start-up support |  | 10.0 |  |  | Construction | 1 | lot | 1500000 | EUR |  |  |  | Class 3 | [9 empty] | 30 | 36

## Resource_Rates
Resource Rates
Hourly rate based resource database. Monthly rate = hourly rate × hours/month.
Role | Discipline | Location | Currency | Hourly Rate | Hours per Month | Monthly Rate | FX Rate | Monthly Rate EUR | Notes
Project Manager | Project Management | Spain | EUR | 130 | 160 |  |  |  | Demo rate
Engineering Manager | Project Management | Spain | EUR | 120 | 160 |  |  |  | Demo rate
Project Controls Lead | Project Management | Spain | EUR | 95 | 160 |  |  |  | Demo rate
Cost Estimator | Project Management | Remote | EUR | 90 | 160 |  |  |  | Demo rate
Planner / Scheduler | Project Management | Remote | EUR | 85 | 160 |  |  |  | Demo rate
Process Engineer | Process | Remote | EUR | 90 | 160 |  |  |  | Demo rate
Procurement Lead | Procurement | Spain | EUR | 90 | 160 |  |  |  | Demo rate
Construction Manager | Construction | Spain | EUR | 115 | 160 |  |  |  | Demo rate
HSE Manager | HSE | Spain | EUR | 85 | 160 |  |  |  | Demo rate
Commissioning Lead | Commissioning | Spain | EUR | 110 | 160 |  |  |  | Demo rate
Document Controller | Project Management | Remote | EUR | 60 | 160 |  |  |  | Demo rate

## Manpower_Plan
Manpower Plan
Dynamic 36-month FTE plan linked to Resource_Rates. Macro can regenerate months from Project_Setup.
Role | Discipline | Monthly Rate EUR | Total FTE-Months | Total Cost EUR
Project Manager | Project Management |  |  |  | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863
Engineering Manager | Project Management |  |  |  | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173
Project Controls Lead | Project Management |  |  |  | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863
Cost Estimator | Project Management |  |  |  | 0.69 | 0.69 | 0.69 | 0.69 | 0.69 | 0.69 | 0.69 | 0.69 | 0.345 | 0.345 | 0.345 | 0.345 | 0.345 | 0.345 | 0.345 | 0.345 | 0.345 | 0.345 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173 | 0.173
Planner / Scheduler | Project Management |  |  |  | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.69 | 0.69 | 0.69 | 0.69 | 0.69 | 0.69
Process Engineer | Process |  |  |  | 2.588 | 2.588 | 2.588 | 2.588 | 2.588 | 2.588 | 2.588 | 2.588 | 2.588 | 2.588 | 2.588 | 2.588 | 1.725 | 1.725 | 1.725 | 1.725 | 1.725 | 1.725 | 1.725 | 1.725 | 1.725 | 1.725 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431
Procurement Lead | Procurement |  |  |  | 0.259 | 0.259 | 0.259 | 0.259 | 0.259 | 0.259 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.173 | 0.173 | 0.173 | 0.173
Construction Manager | Construction |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.431 | 0.431 | 0.431 | 0.431 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.431 | 0.431 | 0.431 | 0.431
HSE Manager | HSE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.604 | 0.604 | 0.604 | 0.604 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.863 | 0.345 | 0.345 | 0.345 | 0.345
Commissioning Lead | Commissioning |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.294 | 1.294 | 1.294 | 1.294 | 1.294 | 1.294 | 1.294 | 1.294
Document Controller | Project Management |  |  |  | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431 | 0.431

## Indirect_Owner_Costs
Indirect Owner Costs
User input layer. Cost_Register must be rebuilt from these sheets via BuildCostRegister.
Item ID | Description | Discipline | WBS | CBS | Cost Category | Cost Type | Quantity | Unit | Unit Rate | Currency | FX Rate | Base Cost | Base Cost EUR | Estimate Basis | Accuracy Low % | Accuracy High % | Low Cost | Most Likely Cost | High Cost | Contingency Eligible | Escalation Eligible | Spend Category | Phase | Start Month | End Month | Spend Curve | Notes
IO-001 | EPCM engineering services |  | 2.0 |  |  | EPCM | 1 | lot | 2200000 | EUR |  |  |  | Class 3 | [9 empty] | 1 | 24
IO-002 | Construction management and supervision |  | 9.0 |  |  | EPCM | 1 | lot | 800000 | EUR |  |  |  | Class 3 | [9 empty] | 14 | 34
IO-003 | Permits, studies and owner reviews |  | 11.0 |  |  | Owner | 1 | lot | 600000 | EUR |  |  |  | Class 3 | [9 empty] | 1 | 18
IO-004 | Freight, logistics and temporary facilities |  | 3.0 |  |  | Freight | 1 | lot | 400000 | EUR |  |  |  | Class 3 | [9 empty] | 8 | 28

## Other_Costs
Other Costs
User input layer. Cost_Register must be rebuilt from these sheets via BuildCostRegister.
Item ID | Description | Discipline | WBS | CBS | Cost Category | Cost Type | Quantity | Unit | Unit Rate | Currency | FX Rate | Base Cost | Base Cost EUR | Estimate Basis | Accuracy Low % | Accuracy High % | Low Cost | Most Likely Cost | High Cost | Contingency Eligible | Escalation Eligible | Spend Category | Phase | Start Month | End Month | Spend Curve | Notes
OT-001 | Capital spares initial holding |  | 12.0 |  |  | Spares | 1 | lot | 400000 | EUR |  |  |  | Class 3 | [9 empty] | 25 | 34
OT-002 | Training and operational readiness |  | 10.0 |  |  | Other | 1 | lot | 200000 | EUR |  |  |  | Class 3 | [9 empty] | 28 | 36
OT-003 | Start-up consumables and temporary support |  | 10.0 |  |  | Other | 1 | lot | 400000 | EUR |  |  |  | Class 3 | [9 empty] | 31 | 36

## Cost_Register
Cost Register
Normalized single source of truth. Populated by BuildCostRegister; demo rows pre-loaded.
Source Sheet | Source Row | Item ID | Description | Discipline | WBS | CBS | Cost Category | Cost Type | Quantity | Unit | Unit Rate | Currency | FX Rate | Base Cost | Base Cost EUR | Estimate Basis | Accuracy Low % | Accuracy High % | Low Cost | Most Likely Cost | High Cost | Contingency Eligible | Escalation Eligible | Spend Category | Phase | Start Month | End Month | Spend Curve | Notes
Equipment_Estimate | 2 | EQ-001 | Process mixer package | Mechanical | 4.0 | EQP | Direct Cost | Equipment | 1 | lot | 2800000 | EUR | 1 | 2800000 | 2800000 | Class 3 | -20% | 0.3 | 2240000 | 2800000 | 3640000 | Yes | Yes | Procurement | Procurement | 8 | 18 | Back Loaded
Equipment_Estimate | 3 | EQ-002 | Process vessels and tanks | Mechanical | 4.0 | EQP | Direct Cost | Equipment | 1 | lot | 3200000 | EUR | 1 | 3200000 | 3200000 | Class 3 | -20% | 0.3 | 2560000 | 3200000 | 4160000 | Yes | Yes | Procurement | Procurement | 6 | 18 | Linear
Equipment_Estimate | 4 | EQ-003 | Pumping and transfer skids | Mechanical | 4.0 | EQP | Direct Cost | Equipment | 1 | lot | 2000000 | EUR | 1 | 2000000 | 2000000 | Class 3 | -20% | 0.3 | 1600000 | 2000000 | 2600000 | Yes | Yes | Procurement | Procurement | 10 | 20 | Back Loaded
Equipment_Estimate | 5 | EQ-004 | Heat exchangers and utility skids | Mechanical | 4.0 | EQP | Direct Cost | Equipment | 1 | lot | 2400000 | EUR | 1 | 2400000 | 2400000 | Class 3 | -20% | 0.3 | 1920000 | 2400000 | 3120000 | Yes | Yes | Procurement | Procurement | 9 | 21 | Back Loaded
Equipment_Estimate | 6 | EQ-005 | Equipment installation auxiliaries | Mechanical | 4.0 | EQP | Direct Cost | Equipment | 1 | lot | 1600000 | EUR | 1 | 1600000 | 1600000 | Class 3 | -20% | 0.3 | 1280000 | 1600000 | 2080000 | Yes | Yes | Construction | Construction | 14 | 27 | Bell Curve
Electrical_Estimate | 2 | EL-001 | MV/LV substation package | Electrical | 7.0 | ELE | Direct Cost | Equipment | 1 | lot | 1400000 | EUR | 1 | 1400000 | 1400000 | Class 3 | -20% | 0.3 | 1120000 | 1400000 | 1820000 | Yes | Yes | Procurement | Procurement | 8 | 18 | Back Loaded
Electrical_Estimate | 3 | EL-002 | MCC and distribution boards | Electrical | 7.0 | ELE | Direct Cost | Equipment | 1 | lot | 1200000 | EUR | 1 | 1200000 | 1200000 | Class 3 | -20% | 0.3 | 960000 | 1200000 | 1560000 | Yes | Yes | Procurement | Procurement | 9 | 20 | Back Loaded
Electrical_Estimate | 4 | EL-003 | Cable trays, cabling and termination | Electrical | 7.0 | ELE | Direct Cost | Bulk Material | 1 | lot | 1600000 | EUR | 1 | 1600000 | 1600000 | Class 3 | -20% | 0.3 | 1280000 | 1600000 | 2080000 | Yes | Yes | Construction | Construction | 15 | 30 | Linear
Electrical_Estimate | 5 | EL-004 | Lighting, earthing and small power | Electrical | 7.0 | ELE | Direct Cost | Construction | 1 | lot | 800000 | EUR | 1 | 800000 | 800000 | Class 3 | -20% | 0.3 | 640000 | 800000 | 1040000 | Yes | Yes | Construction | Construction | 18 | 31 | Linear
Instrumentation_Automation | 2 | IA-001 | PLC/DCS hardware and software | Automation | 8.0 | I&A | Direct Cost | Equipment | 1 | lot | 1200000 | EUR | 1 | 1200000 | 1200000 | Class 3 | -20% | 0.3 | 960000 | 1200000 | 1560000 | Yes | Yes | Procurement | Procurement | 8 | 22 | Back Loaded
Instrumentation_Automation | 3 | IA-002 | Field instrumentation and valves | Instrumentation | 8.0 | I&A | Direct Cost | Equipment | 1 | lot | 1000000 | EUR | 1 | 1000000 | 1000000 | Class 3 | -20% | 0.3 | 800000 | 1000000 | 1300000 | Yes | Yes | Procurement | Procurement | 10 | 25 | Linear
Instrumentation_Automation | 4 | IA-003 | Automation engineering and commissioning | Automation | 8.0 | I&A | Direct Cost | Engineering | 1 | lot | 800000 | EUR | 1 | 800000 | 800000 | Class 3 | -20% | 0.3 | 640000 | 800000 | 1040000 | Yes | Yes | Engineering | Engineering | 4 | 35 | Bell Curve
Bulk_Materials_QTO | 2 | BM-001 | Process piping supply | Piping | 5.0 | BULK | Direct Cost | Bulk Material | 1 | lot | 2100000 | EUR | 1 | 2100000 | 2100000 | Class 3 | -20% | 0.3 | 1680000 | 2100000 | 2730000 | Yes | Yes | Procurement | Procurement | 10 | 25 | Linear
Bulk_Materials_QTO | 3 | BM-002 | Manual and control valves | Piping | 5.0 | BULK | Direct Cost | Bulk Material | 1 | lot | 1100000 | EUR | 1 | 1100000 | 1100000 | Class 3 | -20% | 0.3 | 880000 | 1100000 | 1430000 | Yes | Yes | Procurement | Procurement | 9 | 24 | Back Loaded
Bulk_Materials_QTO | 4 | BM-003 | Insulation, painting and tracing | Piping | 5.0 | BULK | Direct Cost | Bulk Material | 1 | lot | 800000 | EUR | 1 | 800000 | 800000 | Class 3 | -20% | 0.3 | 640000 | 800000 | 1040000 | Yes | Yes | Construction | Construction | 18 | 33 | Linear
Construction_Estimate | 2 | CN-001 | Civil works and foundations | Civil | 6.0 | CIV | Direct Cost | Construction | 1 | lot | 2000000 | EUR | 1 | 2000000 | 2000000 | Class 3 | -20% | 0.3 | 1600000 | 2000000 | 2600000 | Yes | Yes | Construction | Construction | 12 | 26 | Front Loaded
Construction_Estimate | 3 | CN-002 | Mechanical installation works | Construction | 9.0 | CON | Direct Cost | Construction | 1 | lot | 2300000 | EUR | 1 | 2300000 | 2300000 | Class 3 | -20% | 0.3 | 1840000 | 2300000 | 2990000 | Yes | Yes | Construction | Construction | 18 | 31 | Bell Curve
Construction_Estimate | 4 | CN-003 | Electrical installation works | Construction | 9.0 | CON | Direct Cost | Construction | 1 | lot | 1200000 | EUR | 1 | 1200000 | 1200000 | Class 3 | -20% | 0.3 | 960000 | 1200000 | 1560000 | Yes | Yes | Construction | Construction | 18 | 32 | Bell Curve
Construction_Estimate | 5 | CN-004 | Pre-commissioning and start-up support | Commissioning | 10.0 | COM | Direct Cost | Construction | 1 | lot | 1500000 | EUR | 1 | 1500000 | 1500000 | Class 3 | -20% | 0.3 | 1200000 | 1500000 | 1950000 | Yes | Yes | Commissioning | Commissioning | 30 | 36 | Back Loaded
Indirect_Owner_Costs | 2 | IO-001 | EPCM engineering services | Project Management | 2.0 | ENG | Indirect Cost | EPCM | 1 | lot | 2200000 | EUR | 1 | 2200000 | 2200000 | Class 3 | -20% | 0.3 | 1760000 | 2200000 | 2860000 | Yes | Yes | Engineering | Engineering | 1 | 24 | Bell Curve
Indirect_Owner_Costs | 3 | IO-002 | Construction management and supervision | Construction | 9.0 | CON | Indirect Cost | EPCM | 1 | lot | 800000 | EUR | 1 | 800000 | 800000 | Class 3 | -20% | 0.3 | 640000 | 800000 | 1040000 | Yes | Yes | Construction | Construction | 14 | 34 | Linear
Indirect_Owner_Costs | 4 | IO-003 | Permits, studies and owner reviews | Owner | 11.0 | OWN | Owner Cost | Owner | 1 | lot | 600000 | EUR | 1 | 600000 | 600000 | Class 3 | -20% | 0.3 | 480000 | 600000 | 780000 | Yes | Yes | Other | Other | 1 | 18 | Front Loaded
Indirect_Owner_Costs | 5 | IO-004 | Freight, logistics and temporary facilities | Procurement | 3.0 | PROC | Indirect Cost | Freight | 1 | lot | 400000 | EUR | 1 | 400000 | 400000 | Class 3 | -20% | 0.3 | 320000 | 400000 | 520000 | Yes | Yes | Procurement | Procurement | 8 | 28 | Linear
Other_Costs | 2 | OT-001 | Capital spares initial holding | Other | 12.0 | OTH | Other Cost | Spares | 1 | lot | 400000 | EUR | 1 | 400000 | 400000 | Class 3 | -20% | 0.3 | 320000 | 400000 | 520000 | Yes | Yes | Other | Other | 25 | 34 | Back Loaded
Other_Costs | 3 | OT-002 | Training and operational readiness | Owner | 10.0 | COM | Other Cost | Other | 1 | lot | 200000 | EUR | 1 | 200000 | 200000 | Class 3 | -20% | 0.3 | 160000 | 200000 | 260000 | Yes | Yes | Commissioning | Commissioning | 28 | 36 | Linear
Other_Costs | 4 | OT-003 | Start-up consumables and temporary support | Owner | 10.0 | COM | Other Cost | Other | 1 | lot | 400000 | EUR | 1 | 400000 | 400000 | Class 3 | -20% | 0.3 | 320000 | 400000 | 520000 | Yes | Yes | Commissioning | Commissioning | 31 | 36 | Back Loaded
Manpower_Plan | 2 | MP-001 | Project Manager | Project Management | 1.0 | ENG | Manpower Cost | Labour | 1 | lot | 645962.7329 | EUR | 1 | 645962.7329 | 645962.7329 | Class 3 | -20% | 0.3 | 516770.1863 | 645962.7329 | 839751.5528 | Yes | Yes | Engineering | Engineering | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 3 | MP-002 | Engineering Manager | Project Management | 1.0 | ENG | Manpower Cost | Labour | 1 | lot | 417391.3043 | EUR | 1 | 417391.3043 | 417391.3043 | Class 3 | -20% | 0.3 | 333913.0435 | 417391.3043 | 542608.6957 | Yes | Yes | Engineering | Engineering | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 4 | MP-003 | Project Controls Lead | Project Management | 2.0 | ENG | Manpower Cost | Labour | 1 | lot | 472049.6894 | EUR | 1 | 472049.6894 | 472049.6894 | Class 3 | -20% | 0.3 | 377639.7516 | 472049.6894 | 613664.5963 | Yes | Yes | Engineering | Engineering | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 5 | MP-004 | Cost Estimator | Project Management | 2.0 | ENG | Manpower Cost | Labour | 1 | lot | 173913.0435 | EUR | 1 | 173913.0435 | 173913.0435 | Class 3 | -20% | 0.3 | 139130.4348 | 173913.0435 | 226086.9565 | Yes | Yes | Engineering | Engineering | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 6 | MP-005 | Planner / Scheduler | Project Management | 2.0 | ENG | Manpower Cost | Labour | 1 | lot | 337888.1988 | EUR | 1 | 337888.1988 | 337888.1988 | Class 3 | -20% | 0.3 | 270310.559 | 337888.1988 | 439254.6584 | Yes | Yes | Engineering | Engineering | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 7 | MP-006 | Process Engineer | Process | 2.0 | ENG | Manpower Cost | Labour | 1 | lot | 782608.6957 | EUR | 1 | 782608.6957 | 782608.6957 | Class 3 | -20% | 0.3 | 626086.9565 | 782608.6957 | 1017391.3043 | Yes | Yes | Engineering | Engineering | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 8 | MP-007 | Procurement Lead | Procurement | 2.0 | ENG | Manpower Cost | Labour | 1 | lot | 305590.0621 | EUR | 1 | 305590.0621 | 305590.0621 | Class 3 | -20% | 0.3 | 244472.0497 | 305590.0621 | 397267.0807 | Yes | Yes | Engineering | Engineering | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 9 | MP-008 | Construction Manager | Construction | 9.0 | CON | Manpower Cost | Labour | 1 | lot | 317460.3175 | EUR | 1 | 317460.3175 | 317460.3175 | Class 3 | -20% | 0.3 | 253968.254 | 317460.3175 | 412698.4127 | Yes | Yes | Construction | Construction | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 10 | MP-009 | HSE Manager | HSE | 9.0 | CON | Manpower Cost | Labour | 1 | lot | 215873.0159 | EUR | 1 | 215873.0159 | 215873.0159 | Class 3 | -20% | 0.3 | 172698.4127 | 215873.0159 | 280634.9206 | Yes | Yes | Construction | Construction | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 11 | MP-010 | Commissioning Lead | Commissioning | 10.0 | COM | Manpower Cost | Labour | 1 | lot | 182194.617 | EUR | 1 | 182194.617 | 182194.617 | Class 3 | -20% | 0.3 | 145755.6936 | 182194.617 | 236853.0021 | Yes | Yes | Commissioning | Commissioning | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.
Manpower_Plan | 12 | MP-011 | Document Controller | Project Management | 2.0 | ENG | Manpower Cost | Labour | 1 | lot | 149068.323 | EUR | 1 | 149068.323 | 149068.323 | Class 3 | -20% | 0.3 | 119254.6584 | 149068.323 | 193788.8199 | Yes | Yes | Engineering | Engineering | 1 | 36 | Bell Curve | Generated from Resource_Rates and Manpower_Plan profile. FTE scaled to fit 40M demo.

## Estimate_BuildUp
Estimate BuildUp
Aggregations by category, discipline, WBS, phase and eligibility. Reconciles to Cost_Register.
Breakdown Type | Breakdown | Base Cost EUR | Low Cost EUR | Most Likely EUR | High Cost EUR | % of Base | Notes
Cost Category | Direct Cost | [5 empty] | Formula-driven aggregation
Cost Category | Indirect Cost | [5 empty] | Formula-driven aggregation
Cost Category | Owner Cost | [5 empty] | Formula-driven aggregation
Cost Category | Manpower Cost | [5 empty] | Formula-driven aggregation
Cost Category | Other Cost | [5 empty] | Formula-driven aggregation
Discipline | Automation | [5 empty] | Formula-driven aggregation
Discipline | Civil | [5 empty] | Formula-driven aggregation
Discipline | Commissioning | [5 empty] | Formula-driven aggregation
Discipline | Construction | [5 empty] | Formula-driven aggregation
Discipline | Electrical | [5 empty] | Formula-driven aggregation
Discipline | HSE | [5 empty] | Formula-driven aggregation
Discipline | Instrumentation | [5 empty] | Formula-driven aggregation
Discipline | Mechanical | [5 empty] | Formula-driven aggregation
Discipline | Other | [5 empty] | Formula-driven aggregation
Discipline | Owner | [5 empty] | Formula-driven aggregation
Discipline | Piping | [5 empty] | Formula-driven aggregation
Discipline | Process | [5 empty] | Formula-driven aggregation
Discipline | Procurement | [5 empty] | Formula-driven aggregation
Discipline | Project Management | [5 empty] | Formula-driven aggregation
WBS | 1.0 | [5 empty] | Formula-driven aggregation
WBS | 2.0 | [5 empty] | Formula-driven aggregation
WBS | 3.0 | [5 empty] | Formula-driven aggregation
WBS | 4.0 | [5 empty] | Formula-driven aggregation
WBS | 5.0 | [5 empty] | Formula-driven aggregation
WBS | 6.0 | [5 empty] | Formula-driven aggregation
WBS | 7.0 | [5 empty] | Formula-driven aggregation
WBS | 8.0 | [5 empty] | Formula-driven aggregation
WBS | 9.0 | [5 empty] | Formula-driven aggregation
WBS | 10.0 | [5 empty] | Formula-driven aggregation
WBS | 11.0 | [5 empty] | Formula-driven aggregation
WBS | 12.0 | [5 empty] | Formula-driven aggregation
Phase | Engineering | [5 empty] | Formula-driven aggregation
Phase | Procurement | [5 empty] | Formula-driven aggregation
Phase | Construction | [5 empty] | Formula-driven aggregation
Phase | Commissioning | [5 empty] | Formula-driven aggregation
Phase | Other | [5 empty] | Formula-driven aggregation
Contingency Eligible | Yes | [5 empty] | Formula-driven aggregation
Escalation Eligible | Yes | [5 empty] | Formula-driven aggregation
Contingency Eligible | No | [5 empty] | Formula-driven aggregation
Escalation Eligible | No | [5 empty] | Formula-driven aggregation

## Contingency
Contingency
Manual and Monte Carlo contingency are separate from escalation.
Metric | Value | Notes
Selected Method
Base Cost EUR
Manual Contingency % | 12% | Input
Manual Contingency EUR
Monte Carlo P80 |  | From MonteCarlo_Results
Recommended Contingency EUR |  | P80 - Base Cost
Selected Contingency EUR |  | Used in Estimate_Summary
Selected Contingency %

## Escalation
Escalation
Escalation calculated on monthly cash flow, separated from contingency.
Metric | Value | Notes
Annual Escalation Rate |  | Default assumption
Total Base Cash Flow |  | Should equal Base Cost
Total Escalation |  | Sum of monthly escalation
Escalation % of Base |  | Derived
Method | Monthly compounding approximation | (1+annual rate)^(month offset/12)-1

## CashFlow
Cash Flow
Pre-calculated demo cash flow. CalculateCashFlow macro will rebuild from Cost_Register.
Month No | Month | Year | Base Spend EUR | Escalation EUR | Total Spend EUR | Cumulative EUR | Monthly Spend M€ | Cumulative M€ | Cumulative %
1 | 2026-07-01 | 2026 | 85354.6004 | 0 | 85354.6004 | 85354.6004 | 0.085355 | 0.085355 | 0.2042%
2 | 2026-08-01 | 2026 | 92809.5821 | 228.8935 | 93038.4756 | 178393.0759 | 0.093038 | 0.17839 | 0.4269%
3 | 2026-09-01 | 2026 | 104368.0806 | 515.4345 | 104883.5151 | 283276.5911 | 0.10488 | 0.28328 | 0.6778%
4 | 2026-10-01 | 2026 | 123448.3785 | 915.6255 | 124364.004 | 407640.595 | 0.12436 | 0.40764 | 0.9754%
5 | 2026-11-01 | 2026 | 146307.0773 | 1448.6791 | 147755.7564 | 555396.3514 | 0.14776 | 0.5554 | 1.329%
6 | 2026-12-01 | 2026 | 420949.553 | 5216.5432 | 426166.0962 | 981562.4476 | 0.42617 | 0.98156 | 2.349%
7 | 2027-01-01 | 2027 | 454443.7553 | 6766.2842 | 461210.0395 | 1442772.4871 | 0.46121 | 1.4428 | 3.452%
8 | 2027-02-01 | 2027 | 584256.0762 | 10161.4675 | 594417.5438 | 2037190.0309 | 0.59442 | 2.0372 | 4.875%
9 | 2027-03-01 | 2027 | 746427.9359 | 14854.8941 | 761282.83 | 2798472.8609 | 0.76128 | 2.7985 | 6.696%
10 | 2027-04-01 | 2027 | 1131639.9434 | 25367.5904 | 1157007.5338 | 3955480.3946 | 1.157 | 3.9555 | 9.465%
11 | 2027-05-01 | 2027 | 1319351.7066 | 32902.2799 | 1352253.9864 | 5307734.3811 | 1.3523 | 5.3077 | 12.7%
12 | 2027-06-01 | 2027 | 1750815.4587 | 48087.8828 | 1798903.3415 | 7106637.7226 | 1.7989 | 7.1066 | 17%
13 | 2027-07-01 | 2027 | 1907481.2493 | 57224.4375 | 1964705.6868 | 9071343.4094 | 1.9647 | 9.0713 | 21.71%
14 | 2027-08-01 | 2027 | 2108685.9793 | 68617.1855 | 2177303.1648 | 11248646.5742 | 2.1773 | 11.2486 | 26.92%
15 | 2027-09-01 | 2027 | 2364901.3434 | 82976.7748 | 2447878.1182 | 13696524.6924 | 2.4479 | 13.6965 | 32.77%
16 | 2027-10-01 | 2027 | 2524606.4802 | 95025.1375 | 2619631.6177 | 16316156.3102 | 2.6196 | 16.3162 | 39.04%
17 | 2027-11-01 | 2027 | 2689429.345 | 108111.5179 | 2797540.8629 | 19113697.1731 | 2.7975 | 19.1137 | 45.74%
18 | 2027-12-01 | 2027 | 2995802.0413 | 128112.759 | 3123914.8004 | 22237611.9734 | 3.1239 | 22.2376 | 53.21%
19 | 2028-01-01 | 2028 | 2180838.2756 | 98870.1159 | 2279708.3915 | 24517320.3649 | 2.2797 | 24.5173 | 58.67%
20 | 2028-02-01 | 2028 | 2319250.2408 | 111124.3505 | 2430374.5912 | 26947694.9562 | 2.4304 | 26.9477 | 64.48%
21 | 2028-03-01 | 2028 | 1890361.2952 | 95460.1259 | 1985821.4211 | 28933516.3773 | 1.9858 | 28.9335 | 69.23%
22 | 2028-04-01 | 2028 | 1597383.6633 | 84803.7602 | 1682187.4235 | 30615703.8008 | 1.6822 | 30.6157 | 73.26%
23 | 2028-05-01 | 2028 | 1462557.8041 | 81444.5263 | 1544002.3304 | 32159706.1312 | 1.544 | 32.1597 | 76.95%
24 | 2028-06-01 | 2028 | 1439841.4107 | 83928.3147 | 1523769.7254 | 33683475.8566 | 1.5238 | 33.6835 | 80.6%
25 | 2028-07-01 | 2028 | 1234202.9686 | 75162.9608 | 1309365.9294 | 34992841.7861 | 1.3094 | 34.9928 | 83.73%
26 | 2028-08-01 | 2028 | 929723.1566 | 59052.7289 | 988775.8855 | 35981617.6716 | 0.98878 | 35.9816 | 86.1%
27 | 2028-09-01 | 2028 | 790862.7755 | 52307.1769 | 843169.9524 | 36824787.624 | 0.84317 | 36.8248 | 88.12%
28 | 2028-10-01 | 2028 | 680286.4968 | 46782.4666 | 727068.9634 | 37551856.5874 | 0.72707 | 37.5519 | 89.85%
29 | 2028-11-01 | 2028 | 555655.9127 | 39676.4124 | 595332.3251 | 38147188.9125 | 0.59533 | 38.1472 | 91.28%
30 | 2028-12-01 | 2028 | 528936.9907 | 39166.2061 | 568103.1968 | 38715292.1093 | 0.5681 | 38.7153 | 92.64%
31 | 2029-01-01 | 2029 | 448600.23 | 34405.8011 | 483006.0312 | 39198298.1404 | 0.48301 | 39.1983 | 93.79%
32 | 2029-02-01 | 2029 | 424114.0351 | 33654.0122 | 457768.0473 | 39656066.1877 | 0.45777 | 39.6561 | 94.89%
33 | 2029-03-01 | 2029 | 482193.5744 | 39546.2864 | 521739.8609 | 40177806.0486 | 0.52174 | 40.1778 | 96.14%
34 | 2029-04-01 | 2029 | 503084.5179 | 42602.1211 | 545686.639 | 40723492.6876 | 0.54569 | 40.7235 | 97.44%
35 | 2029-05-01 | 2029 | 457819.3451 | 39993.7039 | 497813.049 | 41221305.7367 | 0.49781 | 41.2213 | 98.64%
36 | 2029-06-01 | 2029 | 523208.7203 | 47109.0176 | 570317.7379 | 41791623.4745 | 0.57032 | 41.7916 | 100%

## MonteCarlo_Inputs
Monte Carlo Inputs
Rows copied from Cost_Register where Contingency Eligible = Yes.
Item ID | Description | Low | Most Likely | High | Contingency Eligible | Distribution | Valid | Notes
EQ-001 | Process mixer package | 2240000 | 2800000 | 3640000 | Yes | Triangular | PASS | Demo loaded
EQ-002 | Process vessels and tanks | 2560000 | 3200000 | 4160000 | Yes | Triangular | PASS | Demo loaded
EQ-003 | Pumping and transfer skids | 1600000 | 2000000 | 2600000 | Yes | Triangular | PASS | Demo loaded
EQ-004 | Heat exchangers and utility skids | 1920000 | 2400000 | 3120000 | Yes | Triangular | PASS | Demo loaded
EQ-005 | Equipment installation auxiliaries | 1280000 | 1600000 | 2080000 | Yes | Triangular | PASS | Demo loaded
EL-001 | MV/LV substation package | 1120000 | 1400000 | 1820000 | Yes | Triangular | PASS | Demo loaded
EL-002 | MCC and distribution boards | 960000 | 1200000 | 1560000 | Yes | Triangular | PASS | Demo loaded
EL-003 | Cable trays, cabling and termination | 1280000 | 1600000 | 2080000 | Yes | Triangular | PASS | Demo loaded
EL-004 | Lighting, earthing and small power | 640000 | 800000 | 1040000 | Yes | Triangular | PASS | Demo loaded
IA-001 | PLC/DCS hardware and software | 960000 | 1200000 | 1560000 | Yes | Triangular | PASS | Demo loaded
IA-002 | Field instrumentation and valves | 800000 | 1000000 | 1300000 | Yes | Triangular | PASS | Demo loaded
IA-003 | Automation engineering and commissioning | 640000 | 800000 | 1040000 | Yes | Triangular | PASS | Demo loaded
BM-001 | Process piping supply | 1680000 | 2100000 | 2730000 | Yes | Triangular | PASS | Demo loaded
BM-002 | Manual and control valves | 880000 | 1100000 | 1430000 | Yes | Triangular | PASS | Demo loaded
BM-003 | Insulation, painting and tracing | 640000 | 800000 | 1040000 | Yes | Triangular | PASS | Demo loaded
CN-001 | Civil works and foundations | 1600000 | 2000000 | 2600000 | Yes | Triangular | PASS | Demo loaded
CN-002 | Mechanical installation works | 1840000 | 2300000 | 2990000 | Yes | Triangular | PASS | Demo loaded
CN-003 | Electrical installation works | 960000 | 1200000 | 1560000 | Yes | Triangular | PASS | Demo loaded
CN-004 | Pre-commissioning and start-up support | 1200000 | 1500000 | 1950000 | Yes | Triangular | PASS | Demo loaded
IO-001 | EPCM engineering services | 1760000 | 2200000 | 2860000 | Yes | Triangular | PASS | Demo loaded
IO-002 | Construction management and supervision | 640000 | 800000 | 1040000 | Yes | Triangular | PASS | Demo loaded
IO-003 | Permits, studies and owner reviews | 480000 | 600000 | 780000 | Yes | Triangular | PASS | Demo loaded
IO-004 | Freight, logistics and temporary facilities | 320000 | 400000 | 520000 | Yes | Triangular | PASS | Demo loaded
OT-001 | Capital spares initial holding | 320000 | 400000 | 520000 | Yes | Triangular | PASS | Demo loaded
OT-002 | Training and operational readiness | 160000 | 200000 | 260000 | Yes | Triangular | PASS | Demo loaded
OT-003 | Start-up consumables and temporary support | 320000 | 400000 | 520000 | Yes | Triangular | PASS | Demo loaded
MP-001 | Project Manager | 516770.1863 | 645962.7329 | 839751.5528 | Yes | Triangular | PASS | Demo loaded
MP-002 | Engineering Manager | 333913.0435 | 417391.3043 | 542608.6957 | Yes | Triangular | PASS | Demo loaded
MP-003 | Project Controls Lead | 377639.7516 | 472049.6894 | 613664.5963 | Yes | Triangular | PASS | Demo loaded
MP-004 | Cost Estimator | 139130.4348 | 173913.0435 | 226086.9565 | Yes | Triangular | PASS | Demo loaded
MP-005 | Planner / Scheduler | 270310.559 | 337888.1988 | 439254.6584 | Yes | Triangular | PASS | Demo loaded
MP-006 | Process Engineer | 626086.9565 | 782608.6957 | 1017391.3043 | Yes | Triangular | PASS | Demo loaded
MP-007 | Procurement Lead | 244472.0497 | 305590.0621 | 397267.0807 | Yes | Triangular | PASS | Demo loaded
MP-008 | Construction Manager | 253968.254 | 317460.3175 | 412698.4127 | Yes | Triangular | PASS | Demo loaded
MP-009 | HSE Manager | 172698.4127 | 215873.0159 | 280634.9206 | Yes | Triangular | PASS | Demo loaded
MP-010 | Commissioning Lead | 145755.6936 | 182194.617 | 236853.0021 | Yes | Triangular | PASS | Demo loaded
MP-011 | Document Controller | 119254.6584 | 149068.323 | 193788.8199 | Yes | Triangular | PASS | Demo loaded

## MonteCarlo_Results
Monte Carlo Results
Summary statistics, histogram source and cumulative distribution source. Macro writes data only.
Metric | Value | Bin / Cost Midpoint | Frequency | Cost | Cumulative Probability | Percentile | Cost
Number of Iterations | 10000 | 38417959.679 | 2 | 38260521.7282 | 0% | P50 | 41322505.2063
Mean | 41332120.2184 | 38732835.5806 | 16 | 39626817.3192 | 2% | P80 | 42043336.3011
Standard Deviation | 840756.1212 | 39047711.4822 | 41 | 39875990.2784 | 4% | P90 | 42415053.0192
Minimum | 38260521.7282 | 39362587.3839 | 97 | 40034690.8444 | 6%
Maximum | 44558039.7605 | 39677463.2855 | 203 | 40148072.6234 | 8%
P10 | 40255944.2557 | 39992339.1871 | 443 | 40255944.2557 | 10%
P50 | 41322505.2063 | 40307215.0887 | 709 | 40341378.6417 | 12%
P80 | 42043336.3011 | 40622090.9903 | 1066 | 40425853.8631 | 14%
P90 | 42415053.0192 | 40936966.8919 | 1314 | 40499036.286 | 16%
Recommended Contingency | 2043336.3011 | 41251842.7935 | 1508 | 40570859.0104 | 18%
Run Date/Time | 2026-06-03 14:00:57 | 41566718.6951 | 1394 | 40626516.9739 | 20%
|  | 41881594.5967 | 1190 | 40684821.9787 | 22%
|  | 42196470.4984 | 875 | 40736231.344 | 24%
|  | 42511346.4 | 585 | 40784530.5096 | 26%
|  | 42826222.3016 | 322 | 40837208.3833 | 28%
|  | 43141098.2032 | 134 | 40882502.615 | 30%
|  | 43455974.1048 | 63 | 40932329.0809 | 32%
|  | 43770850.0064 | 27 | 40976987.5595 | 34%
|  | 44085725.908 | 7 | 41025344.0448 | 36%
|  | 44400601.8096 | 4 | 41071714.111 | 38%
|  |  |  | 41119948.1839 | 40%
|  |  |  | 41156467.9601 | 42%
|  |  |  | 41196777.132 | 44%
|  |  |  | 41238961.8595 | 46%
|  |  |  | 41278485.2154 | 48%
|  |  |  | 41322505.2063 | 50%
|  |  |  | 41362737.8135 | 52%
|  |  |  | 41410153.4921 | 54%
|  |  |  | 41455930.9405 | 56%
|  |  |  | 41507480.3586 | 58%
|  |  |  | 41547122.1956 | 60%
|  |  |  | 41589027.8541 | 62%
|  |  |  | 41634142.4913 | 64%
|  |  |  | 41680586.05 | 66%
|  |  |  | 41726109.2669 | 68%
|  |  |  | 41775842.2981 | 70%
|  |  |  | 41823649.3432 | 72%
|  |  |  | 41873827.9173 | 74%
|  |  |  | 41929545.4983 | 76%
|  |  |  | 41985458.8629 | 78%
|  |  |  | 42043336.3011 | 80%
|  |  |  | 42105213.0286 | 82%
|  |  |  | 42170023.694 | 84%
|  |  |  | 42250169.2145 | 86%
|  |  |  | 42331839.8556 | 88%
|  |  |  | 42415053.0192 | 90%
|  |  |  | 42517039.3834 | 92%
|  |  |  | 42639138.4007 | 94%
|  |  |  | 42789509.7436 | 96%
|  |  |  | 43042130.5587 | 98%
|  |  |  | 44558039.7605 | 100%

## Estimate_Summary
Estimate Summary
Executive summary linked to Cost_Register, Escalation, Contingency and MonteCarlo_Results.
Metric | Value
Project Name
Estimate Date
Estimate Class
Base Currency
Project Duration Months
Direct Cost
Indirect Cost
Owner Cost
Manpower Cost
Other Cost
Base Cost
Escalation
Contingency
Total Project Cost
P50
P80
P90
Recommended Contingency
QA Status

## Dashboard
Industrial CAPEX Estimating Dashboard
Final patch: corrected S-curves, clean chart ranges, dropdown/WBS prepopulation and professional layout.
Metric | Value
Base Cost
Escalation
Contingency
Total Project Cost
P50
P80
P90
QA Status

## Charts
Charts & Stable Source Data
Clean chart patch: fixed S-curve source ranges, removed trailing blank points, and moved helper data to hidden columns.
CAPEX Component | Amount M€ | Cost Category | Base Cost M€ | Discipline | Base Cost M€ | Month | Monthly Spend M€ | Cumulative M€ | Cumulative % | Cost Bin M€ | Frequency | Cost M€ | Cumulative Probability | Percentile | Cost M€
Base Cost | 40 | Direct Cost | 31 | Mechanical | 12 | Start | 0 | 0 | 0% | 38.418 | 2 | 38.2605 | 0% | P50 | 41.3225
Escalation | 1.7916 | Indirect Cost | 3.4 | Electrical | 5 | Jul-26 | 0.085355 | 0.085355 | 0.2042% | 38.7328 | 16 | 39.6268 | 2% | P80 | 42.0433
Selected Contingency | 2.0433 | Owner Cost | 0.6 | Construction | 4.6175 | Aug-26 | 0.093038 | 0.17839 | 0.4269% | 39.0477 | 41 | 39.876 | 4% | P90 | 42.4151
Total Project Cost | 43.835 | Other Cost | 1 | Project Management | 4.3963 | Sep-26 | 0.10488 | 0.28328 | 0.6778% | 39.3626 | 97 | 40.0347 | 6%
|  | Manpower Cost | 4 | Piping | 4 | Oct-26 | 0.12436 | 0.40764 | 0.9754% | 39.6775 | 203 | 40.1481 | 8%
|  |  |  | Automation | 2 | Nov-26 | 0.14776 | 0.5554 | 1.329% | 39.9923 | 443 | 40.2559 | 10%
|  |  |  | Civil | 2 | Dec-26 | 0.42617 | 0.98156 | 2.349% | 40.3072 | 709 | 40.3414 | 12%
|  |  |  | Commissioning | 1.6822 | Jan-27 | 0.46121 | 1.4428 | 3.452% | 40.6221 | 1066 | 40.4259 | 14%
|  |  |  | Owner | 1.2 | Feb-27 | 0.59442 | 2.0372 | 4.875% | 40.937 | 1314 | 40.499 | 16%
|  |  |  | Instrumentation | 1 | Mar-27 | 0.76128 | 2.7985 | 6.696% | 41.2518 | 1508 | 40.5709 | 18%
|  |  |  | Process | 0.78261 | Apr-27 | 1.157 | 3.9555 | 9.465% | 41.5667 | 1394 | 40.6265 | 20%
|  |  |  | Procurement | 0.70559 | May-27 | 1.3523 | 5.3077 | 12.7% | 41.8816 | 1190 | 40.6848 | 22%
|  |  |  | Other | 0.4 | Jun-27 | 1.7989 | 7.1066 | 17% | 42.1965 | 875 | 40.7362 | 24%
|  |  |  | HSE | 0.21587 | Jul-27 | 1.9647 | 9.0713 | 21.71% | 42.5113 | 585 | 40.7845 | 26%
[6 empty] | Aug-27 | 2.1773 | 11.2486 | 26.92% | 42.8262 | 322 | 40.8372 | 28%
[6 empty] | Sep-27 | 2.4479 | 13.6965 | 32.77% | 43.1411 | 134 | 40.8825 | 30%
[6 empty] | Oct-27 | 2.6196 | 16.3162 | 39.04% | 43.456 | 63 | 40.9323 | 32%
[6 empty] | Nov-27 | 2.7975 | 19.1137 | 45.74% | 43.7709 | 27 | 40.977 | 34%
[6 empty] | Dec-27 | 3.1239 | 22.2376 | 53.21% | 44.0857 | 7 | 41.0253 | 36%
[6 empty] | Jan-28 | 2.2797 | 24.5173 | 58.67% | 44.4006 | 4 | 41.0717 | 38%
[6 empty] | Feb-28 | 2.4304 | 26.9477 | 64.48% |  |  | 41.1199 | 40%
[6 empty] | Mar-28 | 1.9858 | 28.9335 | 69.23% |  |  | 41.1565 | 42%
[6 empty] | Apr-28 | 1.6822 | 30.6157 | 73.26% |  |  | 41.1968 | 44%
[6 empty] | May-28 | 1.544 | 32.1597 | 76.95% |  |  | 41.239 | 46%
[6 empty] | Jun-28 | 1.5238 | 33.6835 | 80.6% |  |  | 41.2785 | 48%
[6 empty] | Jul-28 | 1.3094 | 34.9928 | 83.73% |  |  | 41.3225 | 50%
[6 empty] | Aug-28 | 0.98878 | 35.9816 | 86.1% |  |  | 41.3627 | 52%
[6 empty] | Sep-28 | 0.84317 | 36.8248 | 88.12% |  |  | 41.4102 | 54%
[6 empty] | Oct-28 | 0.72707 | 37.5519 | 89.85% |  |  | 41.4559 | 56%
[6 empty] | Nov-28 | 0.59533 | 38.1472 | 91.28% |  |  | 41.5075 | 58%
[6 empty] | Dec-28 | 0.5681 | 38.7153 | 92.64% |  |  | 41.5471 | 60%
[6 empty] | Jan-29 | 0.48301 | 39.1983 | 93.79% |  |  | 41.589 | 62%
[6 empty] | Feb-29 | 0.45777 | 39.6561 | 94.89% |  |  | 41.6341 | 64%
[6 empty] | Mar-29 | 0.52174 | 40.1778 | 96.14% |  |  | 41.6806 | 66%
[6 empty] | Apr-29 | 0.54569 | 40.7235 | 97.44% |  |  | 41.7261 | 68%
[6 empty] | May-29 | 0.49781 | 41.2213 | 98.64% |  |  | 41.7758 | 70%
[6 empty] | Jun-29 | 0.57032 | 41.7916 | 100% |  |  | 41.8236 | 72%
[12 empty] | 41.8738 | 74%
[12 empty] | 41.9295 | 76%
[12 empty] | 41.9855 | 78%
[12 empty] | 42.0433 | 80%
[12 empty] | 42.1052 | 82%
[12 empty] | 42.17 | 84%
[12 empty] | 42.2502 | 86%
[12 empty] | 42.3318 | 88%
[12 empty] | 42.4151 | 90%
[12 empty] | 42.517 | 92%
[12 empty] | 42.6391 | 94%
[12 empty] | 42.7895 | 96%
[12 empty] | 43.0421 | 98%
[12 empty] | 44.558 | 100%

## QA_Checks
QA Checks
Automated quality gates. Release must have no Critical/High FAIL.
Check ID | Check Description | Severity | Status | Finding | Recommended Action
QA-001 | Cost_Register is not empty | Critical |  | Cost register row count check | Run BuildCostRegister
QA-002 | Base cost reconciles to Estimate_Summary | High |  | Cost_Register vs Summary Base Cost | Review Cost_Register and Summary formulas
QA-003 | Estimate_BuildUp reconciles to Cost_Register | High |  | BuildUp cost category reconciliation | Review Estimate_BuildUp formulas
QA-004 | Cash Flow reconciles to Base Cost | High |  | Monthly base cash flow reconciliation | Run CalculateCashFlow or review fallback formulas
QA-005 | Base + Escalation + Contingency = TPC | Critical |  | Total project cost arithmetic | Review Estimate_Summary formulas
QA-006 | P10 <= P50 <= P80 <= P90 | High |  | Monte Carlo percentile order | Run Monte Carlo
QA-007 | Summary P80 linked to MC results | High |  | P80 linkage | Avoid hardcoding
QA-008 | Manpower included in Summary | High |  | Manpower rows present | Review Manpower_Plan
QA-009 | No negative base costs | High |  | Cost sign check | Correct inputs
QA-010 | Low <= ML <= High for all rows | High |  | Triangular parameters check | Review Low/ML/High
QA-011 | Charts fed by non-empty ranges | Medium |  | Chart data range check | Run RefreshAll
QA-012 | Duration is not fixed at 36 months | High |  | Duration is formula-driven and can differ from 36 | Test non-demo scenario
QA-013 | No external links intentionally added | High | PASS | Static environment check | Review in Excel Data > Edit Links
Additional Patch QA
Dropdowns applied to input WBS columns | Validation | Input Sheets | PASS | Checked | WBS dropdown range WBS_CBS!A5:A16
WBS prepopulation formulas | Formula | Input Sheets | PASS | Checked | CBS/Discipline/Phase/Category driven from WBS_CBS
Monte Carlo S-curve source | Chart | Charts!P69:Q119 | PASS | Checked | Exact 51 point CDF; no trailing zero rows in chart range
Cash Flow S-curve source | Chart | Charts!G69:J128 | PASS | Checked | Blanks beyond project duration; no artificial zero tail
Empty input rows | Formula | Input Sheets | PASS | Checked | Derived fields return blank when WBS/quantity/rate blank
Workbook formatting | Visual | Tabs | PASS | Checked | Consistent headers/fills and grouped logical sequence retained
Known limitation | Manual | Excel Desktop | INFO | See Release Notes | .bas must be imported in Excel Desktop to make final .xlsm

## Error_Log
Error Log
Macros append controlled errors here. No silent failures.
Timestamp | Macro | Worksheet | Step | Severity | Description | Resolution | User
2026-06-03 14:03:32 | N/A | N/A | Build | Info | Clean build generated without runtime macro execution. | Import VBA .bas to enable macros. | System

## Assumptions_Log
Assumptions Log
Generated as part of the clean rebuild package.
ID | Assumption | Impact | Owner | Status | Notes
ASM-001 | Base currency EUR | All costs converted to EUR | Estimator | Active | FX rates configurable
ASM-002 | Demo project base cost 40 M€ | UAT reference target | Estimator | Active | Generated from demo rows
ASM-003 | Estimate Class 3 default range -20%/+30% | MC low/high inputs | Estimator | Active | Basis_of_Estimate configurable
ASM-004 | Annual escalation 3% | Applied monthly to cash flow | Project Controls | Active | Separate from contingency
ASM-005 | Recommended contingency = P80 - Base Cost | Summary contingency logic | Cost Engineering | Active | Monte Carlo triangular distribution
ASM-006 | Hours per month = 160 | Resource monthly rates | Project Controls | Active | Resource_Rates configurable

## Change_Log
Change Log
Generated as part of the clean rebuild package.
Version | Date | Change | Reason | Status
RC8 Clean Build | 2026-06-03 | Rebuilt workbook structure from scratch | Avoid legacy corruption and macro issues | Complete
RC8 Clean Build | 2026-06-03 | Separated data outputs from charts | Avoid chart movement/rotation/blank charts | Complete
RC8 Clean Build | 2026-06-03 | Added .bas VBA source export | Macro source ready for controlled import | Complete

## Version_History
Version History
Generated as part of the clean rebuild package.
Version | Date | Author | Description | Compatibility
RC8.0 | 2026-06-03 | OpenAI generated build | Clean rebuild package with xlsx workbook + VBA source .bas | Excel desktop; VBA import required for macros

## Validation_Log
Validation Log
Generated as part of the clean rebuild package.
Gate | Check | Result | Evidence | Notes
Gate 1 | Workbook structure created | PASS | 39 sheets created | No legacy sheet copied
Gate 2 | Core data model populated | PASS | 37 Cost_Register rows | Demo loaded
Gate 3 | Base cost reconciliation | PASS | 40,000,000 EUR | Python model check
Gate 4 | Cash flow reconciliation | PASS | 40,000,000 EUR | Python model check
Gate 5 | Chart source ranges populated | PASS | Charts sheet data present | Chart objects attempted in workbook
Gate 6 | Monte Carlo statistics generated | PASS | 10000 iterations | Python simulation with fixed seed
Gate 7 | QA/UAT sheets created | PASS | QA checks sheet populated | Excel formulas should recalculate on open
Gate 8 | Final Excel desktop verification | LIMITATION | Not executable in this environment | User must open in Excel to confirm no repair warnings

## ReadMe
ReadMe - RC8.1 Candidate
Purpose
How to use | Open workbook, import corrected .bas into VBE, save as .xlsm, then run RefreshAll.
Required Excel | Microsoft Excel desktop for Windows recommended for VBA execution.
Data Mode | Use Project_Setup!B18 to mark Blank / Demo / User Data.
Core workflow | LoadDemoProject or enter inputs, BuildCostRegister, CalculateCashFlow, RunMonteCarlo, RunQA.
No hardcoding principle | Change duration, class, currency, cost items and rates from input/configuration sheets.
Macros | VBA writes only controlled output ranges; charts remain pre-positioned and linked to source ranges.
Known limitation | This generated workbook is xlsx; final xlsm conversion requires importing the supplied .bas in Excel.
Known limitation | This environment cannot compile or embed a verified vbaProject.bin without Excel desktop/VBE.

## Functional_Spec
Functional Specification
Generated as part of the clean rebuild package.
Area | From RC7.1 | From Cargill benchmark | Decision for RC8
Project Setup | Compact metadata and setup fields | Formal cover/reporting and project metadata | Use simple Project_Setup plus Control_Panel
Basis of Estimate | AACE-like Class 1-5 ranges | Estimate maturity and quality matrix | Configurable AACE ranges, linked to input formulas
Cost Input | Separate discipline input tabs | Detailed MTO and CBS-driven data | Keep discipline tabs but normalize into Cost_Register
WBS/CBS | Standard list and dropdown concept | Robust CBS reporting and drill-through | Use WBS_CBS config and CBS aggregation
Cost Register | Flat output from macro | Estimate Data as central calculation core | Cost_Register is single source of truth
Dashboard / Charts | Linked charts and MC output areas | Executive report and CBS summaries | Use stable chart data ranges; no VBA chart manipulation
Contingency | Manual/MC concept | 3-point estimate / allowance maturity | Triangular MC; contingency separated from escalation
Escalation / Cash Flow | Basic cashflow sheet | Spend by phase and indexation | Monthly cashflow and escalation by period
QA | QA sheet existed | Audit checks and quality matrix | Explicit Critical/High QA gates

## Technical_Architecture
Technical Architecture
Generated as part of the clean rebuild package.
Layer | Components | Design Rule | Rationale
Presentation | Control_Panel, Summary, Dashboard, Charts | No direct reads from input sheets | Stable reporting
Business Logic | BuildCostRegister, CashFlow, Escalation, Monte Carlo, QA | Header-based VBA only | Avoid wrong-cell writes
Data | Cost_Register, WBS_CBS, FX_Rates, Lists_Config | Flat normalized tables, no subtotals | Maintainable model
Compatibility | xlsx workbook + .bas source | No XML hacking or copied vbaProject | Avoid file corruption
Charts | Pre-positioned chart objects and source tables | Macros update data only | Avoid blank/rotated/overlapping charts

## Data_Flow_Map
Data Flow Map
Generated as part of the clean rebuild package.
Step | Source | Transformation | Destination | Control
1 | Project_Setup / Lists_Config / FX_Rates | Configuration and validation lists | Input sheets | Dropdowns / formulas
2 | Input sheets + Manpower_Plan | Header-based extraction | Cost_Register | BuildCostRegister macro
3 | Cost_Register | SUMIFS aggregation | Estimate_BuildUp | Reconciliation check
4 | Cost_Register | Monthly phasing by start/end/curve | CashFlow | Cash flow QA
5 | CashFlow | Apply monthly escalation factors | Escalation | Escalation QA
6 | Cost_Register | Triangular MC on eligible items | MonteCarlo_Results | Percentile QA
7 | BuildUp/Escalation/Contingency/MC | Executive aggregation | Estimate_Summary / Dashboard / Charts | QA_Checks

## Gap_Analysis
Gap Analysis
Generated as part of the clean rebuild package.
Area | RC7.1 Gap | Cargill Benchmark Strength | RC8 Response
Macro stability | MC/chart macros had wrong-cell/chart manipulation risks | Cargill relies on stable report tabs | Separate macro data output from charts
Corporate reporting | Limited summary/report views | Strong CBS/IPA/DPET reporting | Add Functional_Spec, UAT, QA and dashboard
Complexity | Small and manageable | Very complex with many helper sheets | Use only best-practice concepts, not technical copy
Manpower | Needs robust integration | FTE alignment and labour calcs exist | Resource_Rates + Manpower_Plan included in Cost_Register
File integrity | Prior builds had repair warnings | Mature but heavy template | No legacy XML, no copied sheets, avoid tables where not necessary

## UAT_Report
UAT Report
Generated as part of the clean rebuild package.
Test ID | Scenario | Expected | Actual | Status | Evidence
UAT-001 | Demo base cost equals 40 M€ | 40,000,000 EUR | 40,000,000 EUR | PASS | Python pre-release calculation
UAT-002 | Direct + Indirect + Owner + Manpower + Other = Base Cost | 0 EUR variance | 0 EUR variance | PASS | {"Direct Cost": 31000000.0, "Indirect Cost": 3400000.0, "Owner Cost": 600000.0, "Other Cost": 1000000.0, "Manpower Cost": 4000000.0}
UAT-003 | Monthly cash flow equals Base Cost | 0 EUR variance | 0.00 EUR | PASS | CashFlow sheet data
UAT-004 | Escalation separated from contingency | Separate lines | Escalation and Contingency sheets | PASS | Summary structure
UAT-005 | Monte Carlo percentile order | P10<=P50<=P80<=P90 | 40,255,944 <= 41,322,505 <= 42,043,336 <= 42,415,053 | PASS | MonteCarlo_Results
UAT-006 | Recommended contingency = P80 - Base | 0 EUR variance | 0.00 EUR | PASS | Contingency sheet
UAT-007 | Final Excel open/repair test | No repair warning | Not executed here | LIMITATION | Requires Excel desktop

## Release_Notes
Release Notes RC8.1 Candidate
Status
Important limitation | This environment can export the corrected workbook as .xlsx and the corrected .bas; embedding VBA into a compiled .xlsm requires Excel/VBE.
Core fixes | Estimate_Summary duration, contingency and total project cost formulas corrected.
QA fixes | QA_Checks now uses real formula-driven checks instead of hardcoded PASS where feasible.
No-hardcoding fixes | Project duration, Monte Carlo iterations, standard hours/month and data mode added as configurable parameters.
CashFlow | Workbook includes formula fallback; corrected VBA rebuilds cash flow dynamically from Cost_Register.
Manpower | Monthly rate is linked to Resource_Rates; corrected VBA detects active month range instead of forcing 1-36.
Monte Carlo | Corrected VBA reads iterations from Project_Setup/Control_Panel and writes data only to MonteCarlo_Results.
Charts | Charts sheet source ranges linked to stable calculation ranges; macro does not manipulate charts.
Known limitation | Excel desktop is required to import the .bas and save the workbook as a true .xlsm.
Deferred | Full Cargill MTO suite, IPA metrics and procurement tracker are deferred to a later release.
Validation | Artifact-level formula scan and structural checks performed; final VBA compile/open test must be performed in Excel desktop after import.
RC8.1 Chart Patch | Rebuilt Dashboard and Charts using stable source ranges.
Added | CAPEX waterfall, CAPEX pie breakdown, cash flow S-curve, Monte Carlo S-curve, Monte Carlo distribution, discipline breakdown.
Design control | Macros update data/ranges only; charts are pre-positioned and linked to Charts sheet source tables.
Issue addressed | Removed strange/low-value charts and replaced dense/incorrect chart ranges with M€ normalized sources.
Known limitation | Final macro embedding still requires Excel Desktop to save as .xlsm after importing the .bas module.
Chart patch refinement | Replaced unstable native Waterfall object with a visible waterfall-style CAPEX composition chart to avoid missing/blank charts in exported workbook.
Chart patch refinement | Monte Carlo S-curve and cash flow S-curve now use clean M€ / mmm-yy label sources instead of serial/date/index labels.
Chart patch verification | Charts sheet and Dashboard were rendered and formula errors scanned after patch.
RC8.1 Final Patch - Charts/Dropdown/WBS
Monte Carlo S-Curve | Rebuilt chart source to exact 51-point CDF range; no trailing zero rows.
Project S-Curve | Uses CashFlow source with blanks beyond project duration; no artificial zero tail.
Dropdowns | Applied WBS, currency, basis, yes/no, unit, cost type and spend curve validations to input sheets.
WBS Prepopulation | Discipline, CBS, Cost Category, Phase, Spend Category, Spend Curve and eligibility fields driven by WBS_CBS dictionary.
Empty Rows | Derived formulas return blank for empty rows to avoid artificial zeroes or visible formula errors.
Professional Formatting | Consistent headers, fills, frozen header rows, number formats and source-data blocks.
Dashboard | Rebuilt dashboard charts with stable source ranges.
Charts | Waterfall-style, pie chart, cash flow S-curve, Monte Carlo CDF, histogram and discipline chart included.
Known Limitation | Final VBA embedding still requires Excel Desktop to save as .xlsm and import .bas.